## Summary
📡 MIR REACTOR REPAIR — UNIFIED GANTT (PROD + PTO)
Today: 2026-02-16 ¦ Build: 20260318T104504Z ¦ Switch modes in Summary sheet (AUTO_SCHEDULE_PTO)
Setting | Value | Description
AUTO_SCHEDULE_PTO | OFF | PTO 자동 스케줄링 활성화 (ON=PTO mode, OFF=PROD mode)
AUTO_SHIFT | ON | 날짜 편집 시 하위 태스크 시프트 (PROD mode only)
STOP_AT_FIXED | ON | FIXED 태스크에서 시프트 중단
KEEP_DURATION | ON | Start 편집 시 기간 유지 (End 자동 조정)
SHIFT_WORKDAYS_ONLY | OFF | 평일만 사용 (Mon-Fri, 주말 건너뜀)
REPAINT_MODE | CF | 렌더링 모드: CF (빠름) 또는 PAINT (스냅샷용)
사용 방법: 1. PTO 모드: AUTO_SCHEDULE_PTO=ON → Predecessor/Lag 기반 자동 계산 2. PROD 모드: AUTO_SCHEDULE_PTO=OFF → 수동 날짜 편집 + 하위 시프트 3. VBA 매크로 임포트 후 .xlsm으로 저장 필요 4. 자세한 내용은 README_MIR_Gantt_Unified.md 참조

## Baseline (hidden)
Scenario | Step | Phase | Task | Start | End | Days | Risk | Notes | Predecessor | Lag
BASE | 0 | DOC | CI/PL/CO + Serial stencil verify | 2026-02-17 | 2026-02-18 | 2 | OK | Invoice/PL (HS Code, Arabic/EN), CO by origin. Serial No. must be engraved/stenciled on cargo.
BASE | 1 | PICKUP (FIXED) | LB trailer — Reactor ×2 + Lot 2/3 | 2026-02-19 | 2026-02-19 | 1 | OK | D0 FIXED. LB배차. Free Time 4h FOC, AED 300/hr after. Max 10h cap/day.
BASE | 2 | UAE_REP | DSV Open Yard (simple repair + inspection) | 2026-02-20 | 2026-02-20 | 1 | OK | Repair note + photos + Serial match required. Output links to Temporary Export customs record. | 1 | 0
BASE | 3a | TRANS_OUT | Temporary Export (Repair & Return) | 2026-02-21 | 2026-02-21 | 1 | OK | Broker to submit Fasah 48h before border ETA. Confirm Temporary Export mode + bonding. | 2 | 0
BASE | 3b | TRANS_OUT | UAE → KSA (Ghuwaifat/Al Batha) — 3 days | 2026-02-21 | 2026-02-23 | 3 | HIGH | HIGH RISK: Naql e-document (foreign truck), Fasah Transit Declaration, possible inspection. Detention: AED 300/hr LB; Overnight: AED 2,000/night. 24h free time at each border. | 3a | -1
BASE | 4a | KSA_REP | Temporary Admission (Repair) | 2026-02-24 | 2026-02-24 | 1 | OK | KSA Temporary Entry for repair. Bonding/guarantee amount TBC. Max 12-month validity. Consignee agent required. | 3b | 0
BASE | 4b | KSA_REP | Hitachi / KSA Testing Lab — ~10 days (ASSUMED) | 2026-02-25 | 2026-03-06 | 10 | AMBER | WARNING: TAT NOT confirmed in writing. Must get written commitment from lab/Hitachi. Repair report + test result + part/serial log required for re-import. | 4a | 0
BASE | 5 | TRANS_BACK | Repair & Return re-entry — 3 days | 2026-03-07 | 2026-03-09 | 3 | HIGH | Fasah re-processing. Re-import MUST link to original Temporary Export record (same Serial No.). Mismatch → re-inspection risk. Consignee agent at Sila border required. | 4b | 0
BASE | 6 | FINAL | MRR / MRI + Serial confirm | 2026-03-10 | 2026-03-10 | 1 | OK | Gate pass + unloading + MRR sign-off. Packing condition / Serial No. verified by site engineer. | 5 | 0
BEST | 0 | DOC | All docs ready before pickup | 2026-02-17 | 2026-02-18 | 2 | OK | All documents pre-cleared.
BEST | 1 | PICKUP (FIXED) | LB trailer — no delay | 2026-02-19 | 2026-02-19 | 1 | OK | Fixed date.
BEST | 2 | UAE_REP | Same-day completion assumed | 2026-02-20 | 2026-02-20 | 1 | OK | No scope expansion. | 1 | 0
BEST | 3 | TRANS_OUT | Fasah pre-cleared, Naql ready (2 days) | 2026-02-21 | 2026-02-22 | 2 | OK | Best case: 48h docs submitted in advance, no inspection. | 2 | 0
BEST | 4 | KSA_REP | Arrive Feb 23 · 10d assumed | 2026-02-23 | 2026-03-04 | 10 | OK | Best case arrival Feb 23, complete Mar 04. | 3 | 0
BEST | 5 | TRANS_BACK | Smooth re-import (2 days) | 2026-03-05 | 2026-03-06 | 2 | OK | No mismatch, fast border. | 4 | 0
BEST | 6 | FINAL | Mar 07 | 2026-03-07 | 2026-03-07 | 1 | OK | Best case return. | 5 | 0
WORST | 0 | DOC | Doc Prep + Delays | 2026-02-17 | 2026-02-18 | 2 | OK | Chamber attestation may take extra time.
WORST | 1 | PICKUP (FIXED) | Fixed D0 | 2026-02-19 | 2026-02-19 | 1 | OK | Fixed.
WORST | 2 | UAE_REP | Scope expanded (2 days) WARNING | 2026-02-20 | 2026-02-21 | 2 | HIGH | Scope expands — extra day. | 1 | 0
WORST | 3 | TRANS_OUT | Naql/Fasah/Inspection delays (5d) WARNING | 2026-02-22 | 2026-02-26 | 5 | HIGH | WORST: Naql e-document issue + Fasah physical inspection. Overnight 2× AED 2,000 = AED 4,000+. | 2 | 0
WORST | 4 | KSA_REP | Arrive Feb 27 · 10d assumed | 2026-02-27 | 2026-03-08 | 10 | OK | Worst-case arrival Feb 27. | 3 | 0
WORST | 5 | TRANS_BACK | Serial mismatch / re-inspection risk WARNING | 2026-03-09 | 2026-03-12 | 4 | HIGH | Serial mismatch or document error → UAE border re-inspection. | 4 | 0
WORST | 6 | FINAL | Mar 13 | 2026-03-13 | 2026-03-13 | 1 | OK | Worst case return. | 5 | 0

## LOG
Timestamp | Proc | Sheet | Row | Col | Message

## Gantt_BASE
📡 MIR REACTOR REPAIR — BASE (UNIFIED: PROD + PTO)
Pickup FIXED: 2026-02-19 ¦ TODAY: 2026-02-16 ¦ Timeline: 2026-02-16 → 2026-03-10
# | Phase | Task Description | Start | End | Days | Risk | Notes / Action | Predecessor | Lag(d) | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10
▸ PRE-CLEARANCE & DOCUMENT PREPARATION
0 | DOC | CI/PL/CO + Serial stencil verify | 2026-02-17 | 2026-02-18 | 2 | OK | Invoice/PL (HS Code, Arabic/EN), CO by origin. Serial No. must be engraved/stenciled on cargo.
▸ MIRFA PICKUP → DSV OPEN YARD
1 | PICKUP (FIXED) | LB trailer — Reactor ×2 + Lot 2/3 | 2026-02-19 | 2026-02-19 | 1 | OK | D0 FIXED. LB배차. Free Time 4h FOC, AED 300/hr after. Max 10h cap/day.
▸ DSV OPEN YARD — UAE INTERIM REPAIR
2 | UAE_REP | DSV Open Yard (simple repair + inspection) | 2026-02-20 | 2026-02-20 | 1 | OK | Repair note + photos + Serial match required. Output links to Temporary Export customs record. | 1 | 0
▸ UAE EXIT + TRANSIT → KSA (AL BATHA BORDER)
3a | TRANS_OUT | Temporary Export (Repair & Return) | 2026-02-21 | 2026-02-21 | 1 | OK | Broker to submit Fasah 48h before border ETA. Confirm Temporary Export mode + bonding. | 2 | 0
3b | TRANS_OUT | UAE → KSA (Ghuwaifat/Al Batha) — 3 days | 2026-02-21 | 2026-02-23 | 3 | HIGH | HIGH RISK: Naql e-document (foreign truck), Fasah Transit Declaration, possible inspection. Detention: AED 300/hr LB; Overnight: AED 2,000/night. 24h free time at each border. | 3a | -1
▸ DAMMAM ARRIVAL & MAIN REPAIR
4a | KSA_REP | Temporary Admission (Repair) | 2026-02-24 | 2026-02-24 | 1 | OK | KSA Temporary Entry for repair. Bonding/guarantee amount TBC. Max 12-month validity. Consignee agent required. | 3b | 0
4b | KSA_REP | Hitachi / KSA Testing Lab — ~10 days (ASSUMED) | 2026-02-25 | 2026-03-06 | 10 | AMBER | WARNING: TAT NOT confirmed in writing. Must get written commitment from lab/Hitachi. Repair report + test result + part/serial log required for re-import. | 4a | 0
▸ KSA EXIT + TRANSIT BACK → UAE
5 | TRANS_BACK | Repair & Return re-entry — 3 days | 2026-03-07 | 2026-03-09 | 3 | HIGH | Fasah re-processing. Re-import MUST link to original Temporary Export record (same Serial No.). Mismatch → re-inspection risk. Consignee agent at Sila border required. | 4b | 0
▸ MIRFA FINAL DELIVERY
6 | FINAL | MRR / MRI + Serial confirm | 2026-03-10 | 2026-03-10 | 1 | OK | Gate pass + unloading + MRR sign-off. Packing condition / Serial No. verified by site engineer. | 5 | 0

## Gantt_BEST
📡 MIR REACTOR REPAIR — BEST (UNIFIED: PROD + PTO)
Pickup FIXED: 2026-02-19 ¦ TODAY: 2026-02-16 ¦ Timeline: 2026-02-16 → 2026-03-07
# | Phase | Task Description | Start | End | Days | Risk | Notes / Action | Predecessor | Lag(d) | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07
▸ PRE-CLEARANCE & DOCUMENT PREPARATION
0 | DOC | All docs ready before pickup | 2026-02-17 | 2026-02-18 | 2 | OK | All documents pre-cleared.
▸ MIRFA PICKUP → DSV OPEN YARD
1 | PICKUP (FIXED) | LB trailer — no delay | 2026-02-19 | 2026-02-19 | 1 | OK | Fixed date.
▸ DSV OPEN YARD — UAE INTERIM REPAIR
2 | UAE_REP | Same-day completion assumed | 2026-02-20 | 2026-02-20 | 1 | OK | No scope expansion. | 1 | 0
▸ UAE EXIT + TRANSIT → KSA (BEST: 2 DAYS)
3 | TRANS_OUT | Fasah pre-cleared, Naql ready (2 days) | 2026-02-21 | 2026-02-22 | 2 | OK | Best case: 48h docs submitted in advance, no inspection. | 2 | 0
▸ DAMMAM REPAIR
4 | KSA_REP | Arrive Feb 23 · 10d assumed | 2026-02-23 | 2026-03-04 | 10 | OK | Best case arrival Feb 23, complete Mar 04. | 3 | 0
▸ KSA → UAE RETURN (BEST: 2 DAYS)
5 | TRANS_BACK | Smooth re-import (2 days) | 2026-03-05 | 2026-03-06 | 2 | OK | No mismatch, fast border. | 4 | 0
▸ MIRFA FINAL DELIVERY
6 | FINAL | Mar 07 | 2026-03-07 | 2026-03-07 | 1 | OK | Best case return. | 5 | 0

## Gantt_WORST
📡 MIR REACTOR REPAIR — WORST (UNIFIED: PROD + PTO)
Pickup FIXED: 2026-02-19 ¦ TODAY: 2026-02-16 ¦ Timeline: 2026-02-16 → 2026-03-13
# | Phase | Task Description | Start | End | Days | Risk | Notes / Action | Predecessor | Lag(d) | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13
▸ PRE-CLEARANCE & DOCUMENT PREPARATION
0 | DOC | Doc Prep + Delays | 2026-02-17 | 2026-02-18 | 2 | OK | Chamber attestation may take extra time.
▸ MIRFA PICKUP → DSV OPEN YARD
1 | PICKUP (FIXED) | Fixed D0 | 2026-02-19 | 2026-02-19 | 1 | OK | Fixed.
▸ DSV OPEN YARD — UAE INTERIM REPAIR (EXTENDED)
2 | UAE_REP | Scope expanded (2 days) WARNING | 2026-02-20 | 2026-02-21 | 2 | HIGH | Scope expands — extra day. | 1 | 0
▸ UAE EXIT + TRANSIT → KSA (WORST: 5 DAYS)
3 | TRANS_OUT | Naql/Fasah/Inspection delays (5d) WARNING | 2026-02-22 | 2026-02-26 | 5 | HIGH | WORST: Naql e-document issue + Fasah physical inspection. Overnight 2× AED 2,000 = AED 4,000+. | 2 | 0
▸ DAMMAM REPAIR
4 | KSA_REP | Arrive Feb 27 · 10d assumed | 2026-02-27 | 2026-03-08 | 10 | OK | Worst-case arrival Feb 27. | 3 | 0
▸ KSA → UAE RETURN (WORST: 4 DAYS)
5 | TRANS_BACK | Serial mismatch / re-inspection risk WARNING | 2026-03-09 | 2026-03-12 | 4 | HIGH | Serial mismatch or document error → UAE border re-inspection. | 4 | 0
▸ MIRFA FINAL DELIVERY
6 | FINAL | Mar 13 | 2026-03-13 | 2026-03-13 | 1 | OK | Worst case return. | 5 | 0